BankEase Customer Retention & Churn Analysis

Project Charter

Project Type: Business Analysis Capstone Project
Industry: Retail Banking / FinTech
Organization: BankEase Financial Services
Role: Business Analyst
Project Status: Proposed
Methodology: Agile-inspired Business Analysis Approach

1. Project Overview

BankEase Financial Services is a fictional mid-sized Indian digital-first retail banking organization serving approximately 100,000 retail customers.

The organization has experienced continued customer acquisition; however, a significant proportion of customers become inactive or discontinue using banking services after several months.

Management currently relies on periodic reports and information from different business functions to understand customer behavior. Because customer information is distributed across multiple sources, the organization has limited visibility into the factors contributing to customer churn and inactivity.

This project aims to analyze customer behavior, identify patterns associated with churn, understand stakeholder requirements, and design a data-driven approach for identifying and engaging customers who may be at risk of becoming inactive.

2. Business Problem

BankEase currently faces a customer retention challenge.

Although the bank continues to acquire new customers, approximately 18% of the customer base in the project scenario is classified as inactive or churned.

The organization does not currently have a centralized, data-driven approach for:

- Understanding the major factors associated with customer churn

- Identifying customer segments with higher churn rates

- Detecting potentially at-risk customers early

- Connecting customer behavior with complaints and satisfaction

- Providing management with interactive retention analytics

As a result, customer retention activities are primarily reactive rather than proactive.

3. Business Need

BankEase requires a structured analytical and business-analysis approach to understand customer churn and improve the organization's ability to identify retention opportunities.

The business needs a solution that can:

- Consolidate relevant customer behavior information for analysis.

- Identify patterns and factors associated with churn.

- Segment customers according to relevant behavioral characteristics.

- Provide management with clear and interactive churn analytics.

- Support Customer Success and Marketing teams in prioritizing retention activities.

- Establish a future-state process for proactive customer retention.

4. Project Goal

The goal of this project is to investigate customer churn at BankEase, identify significant patterns and customer segments associated with inactivity, and design a data-driven customer retention approach supported by business requirements, process improvements, and analytics.

5. Project Objectives

The project will pursue the following objectives:

Objective 1: Analyze Customer Churn

Determine the overall customer churn/inactivity rate and understand how it varies across customer segments.

Objective 2: Identify Churn Drivers

Analyze relationships between customer churn and factors such as:

- Customer tenure

- Transaction frequency

- Account type

- Number of banking products

- Customer satisfaction

- Complaints

- Mobile banking usage

- Customer service interactions

Objective 3: Identify High-Risk Segments

Identify customer groups that demonstrate higher levels of inactivity or churn.

Objective 4: Improve Business Visibility

Design an interactive Power BI dashboard that enables business stakeholders to monitor and investigate customer retention metrics.

Objective 5: Improve the Retention Process

Analyze the current customer retention process and design a proposed future-state process that enables earlier identification and engagement of potentially at-risk customers.

Objective 6: Provide Business Recommendations

Develop evidence-based recommendations that management can evaluate as potential customer retention initiatives.

6. Key Business Questions

The analysis will address the following business questions:

Customer Behavior

- Which customer segments have the highest churn rates?

- Does customer tenure have a relationship with churn?

- Does transaction frequency differ significantly between retained and churned customers?

- Does mobile banking usage appear to influence customer retention?

Customer Experience

- Is there a relationship between customer complaints and churn?

- Does customer satisfaction differ between retained and churned customers?

- Do repeated customer-service interactions correspond with higher churn?

Product Usage

- Do customers using multiple banking products demonstrate different retention patterns?

- Which account types demonstrate higher levels of churn or inactivity?

Business Decision-Making

- Which customer segments should be considered for retention interventions?

- What type of retention action could be considered for each major segment?

- What KPIs should management monitor to evaluate retention performance?

7. Project Scope

7.1 In Scope

The project will include:

- Customer churn analysis

- Customer segmentation

- Customer behavior analysis

- Transaction behavior analysis

- Customer satisfaction analysis

- Complaint analysis

- Mobile banking usage analysis

- Stakeholder analysis

- Requirements gathering

- Business requirements documentation

- Functional and non-functional requirements

- Current-state process analysis

- Future-state process design

- SQL-based data analysis

- Power BI dashboard development

- Business recommendations

- Implementation roadmap

- Risks, assumptions, and constraints

- Requirements Traceability Matrix

7.2 Out of Scope

The project will not include:

- Development of a production banking application

- Core banking system development

- Payment processing

- Loan approval or underwriting

- Real-time banking infrastructure

- Automated SMS or email communication

- Production deployment

- Actual customer intervention

- Production-grade predictive AI implementation

- Integration with live banking systems

8. Key Stakeholders

| Stakeholder | Role in Project | Primary Interest |
| --- | --- | --- |
| Head of Retail Banking | Executive Sponsor | Business performance and retention |
| Customer Success Manager | Process Owner | Customer retention |
| Marketing Manager | Business Stakeholder | Customer segmentation and campaigns |
| Customer Service Manager | Business Stakeholder | Complaints and customer experience |
| Data Analyst | Technical Stakeholder | Data preparation and analysis |
| IT Manager | Technical Stakeholder | Data availability and feasibility |
| Business Analyst | Project Analyst | Requirements, analysis and solution design |
| Customers | End Users | Banking experience and service quality |

9. Proposed Solution

The project will propose a centralized analytical approach for understanding customer churn.

The proposed solution will consist of:

Customer Data

↓

Data Cleaning & Preparation

↓

SQL-Based Analysis

↓

Customer Segmentation

↓

Churn & Behavior Analysis

↓

Power BI Dashboard

↓

At-Risk Customer Identification

↓

Retention Recommendations

↓

Future-State Retention Process

The proposed solution is intended to support business decision-making rather than replace human decision-making.

10. Key Deliverables

The project will produce the following deliverables:

- Project Charter

- Business Case

- Stakeholder Analysis

- Stakeholder Interview Documentation

- Business Requirements Document

- Functional Requirements

- Non-Functional Requirements

- User Stories

- Acceptance Criteria

- Requirements Traceability Matrix

- As-Is Process Map

- Gap Analysis

- To-Be Process Map

- Data Dictionary

- Cleaned Dataset

- SQL Analysis

- Power BI Dashboard

- Business Recommendations

- Implementation Roadmap

- Final Capstone Report

- Final Presentation

- GitHub Portfolio Repository

11. Success Metrics

The following KPIs will be used to evaluate the proposed solution and monitor customer retention:

| KPI | Definition |
| --- | --- |
| Customer Churn Rate | Percentage of customers classified as churned/inactive |
| Customer Retention Rate | Percentage of customers retained during a defined period |
| Active Customer Rate | Percentage of customers demonstrating active usage |
| High-Risk Customer Count | Number of customers meeting defined risk criteria |
| Average Transaction Frequency | Average number of transactions per customer |
| Complaint Rate | Percentage of customers raising complaints |
| Average Satisfaction Score | Average reported customer satisfaction |
| Retention Campaign Response Rate | Percentage of targeted customers responding to retention initiatives |

12. Scenario Business Target

For the purpose of this capstone scenario, BankEase management has proposed a target of reducing customer churn/inactivity from approximately 18% to 15% within 12 months following implementation of an appropriate retention program.

This target is a fictional management target created for the case study and does not represent an actual BankEase business result.

The capstone will focus on identifying opportunities and designing a proposed solution; it will not claim that the target has been achieved.

13. Assumptions

The project is based on the following assumptions:

- Customer transaction information is available for analysis.

- Customer records can be linked using a unique customer identifier.

- Customer service and complaint records can be associated with customers.

- Customer satisfaction information is available.

- Mobile banking usage data can be measured.

- Historical customer activity data is sufficiently available for analysis.

- The portfolio dataset represents a simplified version of operational banking data.

- Appropriate authorization would be required for real-world use of customer information.

- The project dataset will be synthetic or sourced from an appropriate publicly available dataset.

14. Constraints

The project may be affected by the following constraints:

- Missing customer data

- Inconsistent data formats

- Duplicate records

- Incomplete historical information

- Limited customer feedback data

- Differences between operational systems

- Limited ability to determine the actual cause of churn

- Synthetic data limitations in the portfolio environment

Correlation identified during analysis will not automatically be treated as proof of causation.

15. Key Risks

| Risk | Potential Impact | Mitigation |
| --- | --- | --- |
| Missing data | Reduced analytical accuracy | Data-quality assessment and documented assumptions |
| Duplicate records | Incorrect customer counts | Data-cleaning rules |
| Inconsistent data | Incorrect analysis | Standardization and validation |
| Misinterpretation of correlation | Incorrect business conclusions | Clearly distinguish correlation from causation |
| Synthetic dataset limitations | Reduced real-world representation | Clearly document assumptions |
| Scope expansion | Project delays | Maintain defined project scope |

16. High-Level Project Approach

The project will follow an Agile-inspired Business Analysis approach:

Phase 1 - Business Understanding

Define the business problem, objectives, stakeholders, scope, and success criteria.

Phase 2 - Stakeholder Discovery

Conduct simulated stakeholder interviews and identify stakeholder needs and pain points.

Phase 3 - Requirements Analysis

Translate stakeholder needs into business, functional, and non-functional requirements.

Phase 4 - Process Analysis

Document the current-state process, identify gaps, and design a proposed future-state process.

Phase 5 - Data Analysis

Prepare the dataset and perform analysis using Excel and SQL.

Phase 6 - Visualization

Develop an interactive Power BI dashboard for management and operational stakeholders.

Phase 7 - Solution Recommendations

Translate analytical findings into actionable business recommendations.

Phase 8 - Final Documentation

Create the final case study, implementation roadmap, presentation, and GitHub portfolio.

17. Project Outcome

At the conclusion of the project, BankEase management should have:

- A clearer understanding of customer churn patterns

- Identified customer segments associated with higher churn

- A documented set of business and functional requirements

- An improved understanding of the current retention process

- A proposed future-state retention process

- An interactive customer retention dashboard

- A set of evidence-based business recommendations

- A roadmap for potential implementation

18. Project Disclaimer

This project is a fictional Business Analysis portfolio case study created to demonstrate practical Business Analyst skills.

BankEase Financial Services, its business figures, stakeholders, processes, and scenario assumptions are fictional unless a specific external dataset or source is explicitly referenced.

No real customer personal information will be used.

The project demonstrates analytical and business-analysis methodology rather than representing an actual banking implementation.