## Sheet1
Column | Header
A | Stakeholder ID
B | Stakeholder
C | Department
D | Role
E | Project Interest
F | Project Influence
G | Key Concerns
H | Information Needed
I | Communication Frequency
J | Engagement Strategy

## Sheet2
ID | Stakeholder | Department | Role | Interest | Influence | Key Concerns | Information Needed | Communication | Engagement Strategy
ST-01 | Head of Retail Banking | Retail Banking | Executive Sponser | High | High | Churn, business performance, retention | KPIs, trends, segments, business impact | Monthly | Manage Closely
ST-02 | Customer Success Manager | Customer Success | Process Owner | High | High | Reactive retention, at-risk customers | Engagement indicators, customer segments, risk indicators | Weekly | Manage Closely
ST-03 | Marketing Manager | Marketing | Bussiness Stakeholder | High | Medium | Generic campaigns, limited segmentation | Behavioral segments, product usage, campaign metrics | Bi- Weekly | Keep Satisfied
ST-04 | Customer Service Manager | Customer Service | Bussiness Stakeholder | High | Medium | Complaints, customer dissatisfaction | Complaint history, satisfaction, service trends | Bi- Weekly | Keep Satisfied
ST-05 | Data Analyst | Data & Analytics | Technical Stakeholder | High | Medium | Data inequality, inconsistent data | Data definitions, data sources, KPI calculations | Weekly | Manage Closely
ST-06 | IT Manager | IT | Technical Stakeholder | Medium | High | Data availability, feasibility, security | Technical requirements, data access requirements | As Required | Keep Satisfied
ST-07 | Bussiness Analyst | Bussiness Analysis | Project Analyst | High | High | Requirements, scope, stakeholder allignment | Stakeholder needs, business rules, process information | Continous | Manage Closely
ST-08 | Customers | Retail Banking | End Users | High | Low | Service experience, usability, satisfaction | Customer experience information, feedback | Periodic | Keep Informed

## Power_Interest_Matrix
| High Interest | Low Interest
High Influence | Manage Closely | Keep Satisfied
Low Influence | Keep Informed | Monitor

## Stakeholder_Priorities
Stakeholder | Priority | Why?
Head of Retail Banking | Critical | Executive sponsor and business decision-maker
Customer Success Manager | Critical | Owns the retention process
Data Analyst | High | Provides and validates analytical data
Business Analyst | Critical | Responsible for requirements and stakeholder alignment
Marketing Manager | High | Uses customer segmentation for campaigns
Customer Service Manager | High | Provides customer experience information
IT Manager | High | Supports data access and technical feasibility
Customers | Medium | End-user perspective and feedback